## Sheet1
Task | Start Date | End Date | Duration | Resources
Problem statement finalization | 2024-01-08 | 2024-01-15 | 8 | Atharva,Ketan,Nikhil
Project Plan | 2024-01-16 | 2024-01-31 | 16 | Atharva
Requirement Analysis | 2024-02-01 | 2024-02-05 | 5 | Ketan,Atharva
Functional Flow and Screens Identification | 2024-02-06 | 2024-02-09 | 4 | Nikhil,Atharva
Creating Mocks for each of the Screens Identified | 2024-02-10 | 2024-02-13 | 4 | Ketan
Web Scraping POC | 2024-02-13 | 2024-02-18 | 6 | Nikhil
Database Modelling | 2024-02-19 | 2024-02-29 | 10 | Atharva
Data population using Web scraping | 2024-03-01 | 2024-03-10 | 10 | Atharva,Nikhil
Price comparision functionality | 2024-03-11 | 2024-03-20 | 10 | Atharva,Ketan,Nikhil
Frontend | 2024-03-21 | 2024-03-31 | 10 | Ketan,Nikhil
Testing | 2024-04-01 | 2024-04-10 | 10 | Atharva,Ketan,Nikhil
Documentation and project report | 2024-04-11 | 2024-04-15 | 5 | Atharva,Ketan,Nikhil